## Slide 1
KAILA
Detailed To-Do List + Complete Templates and Forms
Readable PowerPoint version with larger text and the full forms/templates pack included.
Validation first
Build proof before building the app.
Provider supply first
Recruit providers before client launch.
Trust first
Use levels, ratings, and records.
Prepared for the first KAILA Gingoog Concierge Pilot
KAILA
01

## Slide 2
Guide
How to Use This Deck
Designed to be readable on-screen and useful as an operations checklist.
Guide
02
Use Section 1 as the startup execution guide for the first 90 days.
Use Section 2 as the complete templates/forms pack for Google Forms, Google Sheets, Messenger, and meetings.
Copy each form field exactly, then adjust local wording if needed.
Keep this deck as the operating playbook during the concierge pilot.

## Slide 3
Section 1
Execution Roadmap
90-day sequence
Founder alignment
Provider-first pilot
Manual matching workflow
Metrics and go/no-go decision
KAILA
03

## Slide 4
Guide
The Main Rule
KAILA starts as a validation project before it becomes a software project.
Guide
04
Risky path
Full app → no users → wasted time
Right path
Manual pilot → evidence → focused MVP
First proof needed
Requests, provider offers, completed/strongly matched jobs, ratings, manageable disputes.

## Slide 5
Guide
90-Day Starting Roadmap
A disciplined sequence for turning KAILA into evidence.
Guide
05
1
Days 1–7
Foundation: scope, forms, sheets, scripts
2
Days 8–21
Recruit providers and build supply
3
Days 22–30
Validate client demand
4
Days 31–75
Run concierge pilot
5
Days 76–90
Review and decide
Record every step: request time, providers contacted, response time, offers, selected provider, agreed amount, completion, ratings, and issues.

## Slide 6
Checklist
Phase 0: Founder Alignment
Agree on the operating philosophy before asking anyone to join.
Checklist
06
☐ Write: KAILA is validation first, software second.
☐ Agree that the first version is manual, free, local, and provider-first.
☐ Define KAILA as a local trust and service-matching system, not just an app.
☐ Name the first pilot owner and backup owner.
☐ List founder roles even if one person handles several roles.
☐ Create a simple decision log for major choices.
☐ Agree that provider trust levels will be used from the start.
☐ Agree not to monetize until usage and trust are proven.

## Slide 7
Guide
Phase 1: Define the First Pilot
Keep the first version narrow enough to operate and measure.
Guide
07
Field
Input / Notes
Pilot area
Gingoog City or selected barangay cluster. List exact barangays before launch.
Clients
Households, renters, homeowners, students, small businesses, offices, and local shops.
Providers
Skilled workers, repair technicians, freelancers, small shops, experienced workers, certified providers if available.
Duration
30–45 active matching days, plus preparation and review days.
Pricing
Free for clients and providers during validation. No commission or subscription yet.
Primary goal
Learn fast without creating a heavy operation.

## Slide 8
Guide
Choose 5–8 Starting Categories
Select practical, common, and manageable local services.
Guide
08
Appliance repair
Urgent household need
Plumbing
Leaks, clogs, toilets, faucets
Electrical
Common but safety-sensitive
Computer repair
Students, offices, homes
Motorcycle repair
Local mobility need
Carpentry / maintenance
Small repairs and installs
Cleaning / odd jobs
Flexible supply
Digital services
Layouts, designs, basic tech

## Slide 9
Checklist
Phase 2: Build the Manual System
Use simple tools first. Let the process teach the software.
Checklist
09
☐ Create Facebook Page for public presence.
☐ Create Provider Signup Form for supply intake.
☐ Create Client Request Form for demand intake.
☐ Create Provider Sheet as the supply database.
☐ Create Request Tracker for job evidence.
☐ Create Completed Job Log for final outcomes.
☐ Create Dispute Log for issues and resolutions.
☐ Use Messenger for manual matching and updates.

## Slide 10
Checklist
Phase 3: Recruit Providers First
Clients will only trust KAILA if relevant providers are already available.
Checklist
10
☐ Build a 100-provider lead list.
☐ Contact the first 20 provider leads on Day 7.
☐ Ask every provider for two referrals.
☐ Group providers by category and barangay.
☐ Collect service area, availability, price range, and work samples.
☐ Target 50 listed providers before heavy client promotion.
☐ Make sure each request can be sent to 3–5 relevant providers.
☐ Mark fast-reply providers as priority providers.

## Slide 11
Guide
Provider Pitch Must Answer
Keep the provider message simple and practical.
Guide
11
Will this help me get clients?
Explain that KAILA forwards relevant local requests.
Is it free?
Confirm the pilot is free while validation is ongoing.
Can I accept or decline?
Providers can accept, decline, or counter-offer.
Can I control my price?
Providers submit their own offer or schedule.

## Slide 12
Guide
Phase 4: Make Trust Visible
Do not present all providers as equally verified.
Guide
12
Field
Input / Notes
Level 1: Listed
Basic profile submitted. Not yet verified.
Level 2: Identity Verified
ID or basic identity check completed with consent.
Level 3: Work Verified
Work samples, references, or completed pilot jobs.
Level 4: Top Rated
Good ratings, fast response, completed jobs, low dispute rate.
Level 5: Certified / Business Verified
Certificate, permit, shop, training proof, or recognized business background.

## Slide 13
Checklist
Phase 5: Validate Client Demand
Listen for repeated pain points before launching publicly.
Checklist
13
☐ Prepare client survey form.
☐ Collect 100 resident responses if possible.
☐ Get at least 30–50 strong responses before first active requests.
☐ Record hardest-to-find services.
☐ Record common trust problems.
☐ Record pricing confusion.
☐ Record response-time frustrations.
☐ List top service categories requested by clients.

## Slide 14
Guide
Client Pain Points to Track
Repeated pain points are stronger than one-off opinions.
Guide
14
“Lisod mangita ug kasaligan”
Trust problem
“Walay klaro nga presyo”
Pricing problem
“Dugay mu-reply”
Response problem
“Referral ra gyud mi magsalig”
Informal discovery
“Wala ko kabalo kinsa duol”
Location discovery

## Slide 15
Guide
Phase 6: Run the Concierge Pilot
The first KAILA workflow should be manual, measurable, and repeatable.
Guide
15
1
Client request
Client submits form or messages page.
2
KAILA checks
Clarify category, location, budget, urgency.
3
Forward request
Send to 3–5 matching providers.
4
Offers received
Record price, availability, response time.
5
Client chooses
Share comparison and confirm choice.
6
Job + ratings
Track completion and collect ratings.
Record every step: request time, providers contacted, response time, offers, selected provider, agreed amount, completion, ratings, and issues.

## Slide 16
Guide
Phase 7: Track the Right Metrics
The pilot must be judged by evidence, not excitement.
Guide
16
Field
Input / Notes
Active providers
Shows supply strength and category readiness.
Requests
Shows demand from clients.
Response rate
Shows provider seriousness.
Offers per request
Shows marketplace activity.
Completed jobs
Shows actual value created.
Ratings
Shows trust and feedback behavior.
Disputes
Shows risk and quality problems.
GMV
Total peso value of completed jobs through KAILA.

## Slide 17
Guide
Phase 8: Go / No-Go Decision
After the pilot, choose the next move based on evidence.
Guide
17
Field
Input / Notes
Proceed to MVP
Real requests, provider response, 15+ completed/strongly matched jobs, ratings accepted, disputes manageable.
Narrow scope
Only 1–2 categories work strongly. Focus on winning categories instead of stopping.
Redesign / pause
Providers refuse, clients avoid posting, trust barriers are too high, or operations cannot support matching.

## Slide 18
Guide
Phase 9: Build MVP Only After Strong Signals
The MVP should digitize the proven manual workflow.
Guide
18
Field
Input / Notes
Client side
Register, post request, compare offers, choose provider, confirm completion, rate provider.
Provider side
Create profile, view matching requests, send offer, update job status, rate client.
Admin side
Manage users, verify providers, track jobs, handle disputes, view reports.
Postpone
In-app payments, GPS tracking, native apps, complex AI matching, large-scale automation.

## Slide 19
Guide
Phase 10: Monetize Slowly
Do not charge until providers feel real value.
Guide
19
Field
Input / Notes
1. Free pilot
Build trust, track behavior, and prove the service flow.
2. Visibility products
Premium profiles, featured listings, badge display, provider highlights.
3. Lead / transaction revenue
Lead credits, subscriptions, small commission, business accounts only after usage is proven.
Recommended first paid product
Provider visibility package, not commission.

## Slide 20
Guide
Founder Roles Must Be Clear
Even if one person holds several roles, responsibilities should be named.
Guide
20
Product / Tech
Vision, MVP planning, technical direction
Provider Acquisition
Recruitment, onboarding, provider feedback
Operations
Matching, support, disputes, tracking
Marketing / Community
Facebook page, client education, local partners
Finance / Admin
Budget, records, reports, compliance prep
Business Strategy
Model, partnerships, pilot decisions

## Slide 21
Checklist
Protect KAILA Early
Treat data, brand, provider records, and internal strategy carefully.
Checklist
21
☐ Limit access to provider list.
☐ Share only necessary client details with providers.
☐ Ask permission before using photos/videos publicly.
☐ Keep ratings and disputes factual.
☐ Organize brand files, forms, sheets, reports, and pitch materials.
☐ Clarify ownership of code and source files.
☐ Store verification materials securely.
☐ Use request IDs and provider IDs instead of informal filenames.

## Slide 22
Checklist
Weekly Operating Rhythm
Review evidence, improve the workflow, and assign next actions.
Checklist
22
☐ Update provider sheet, request tracker, job log, and dispute log.
☐ Compute weekly metrics: providers, requests, offers, jobs, ratings, disputes, GMV.
☐ Identify top 3 lessons and top 3 problems.
☐ Review strongest and weakest categories.
☐ Assign owners and deadlines for next actions.
☐ Update scripts, forms, and rules based on actual problems.
☐ Document decisions clearly.
☐ Prepare a short weekly summary.

## Slide 23
Checklist
First 7 Days: Exact Starter Checklist
Start immediately without building the app.
Checklist
23
☐ Day 1: Decide pilot area, categories, client groups, provider groups, and free-pilot policy.
☐ Day 2: Create Facebook page, add description, contact details, category list, and pinned post.
☐ Day 3: Create provider form and provider database sheet.
☐ Day 4: Create client request form, request tracker, job log, and dispute log.
☐ Day 5: Write rules, scripts, matching message, offer comparison, and rating templates.
☐ Day 6: Build 100-provider lead list.
☐ Day 7: Contact first 20 provider leads and start onboarding.

## Slide 24
Guide
Recommended First Move
KAILA Gingoog Concierge Pilot
Guide
24
50 providers
Recruit and categorize
100 client responses
Survey and validate demand
30 real requests
Collect during pilot
15 completed / matched jobs
Minimum strong evidence target
5–8 categories
Narrow and manageable
30–45 days
Active matching period

## Slide 25
Section 2
Complete Templates and Forms Pack
Provider forms
Client request forms
Tracking sheets
Scripts and messages
Weekly reports and scorecards
KAILA
25

## Slide 26
Templates
Forms Pack Overview
Copy these templates into Google Forms, Google Sheets, Messenger, and meeting notes.
Templates
26
Provider Signup Form: collects provider identity, services, availability, pricing, proof, and consent.
Client Request Form: collects demand details for matching.
Tracking Sheets: provider database, request tracker, completed job log, dispute log.
Survey + Interview Forms: collect validation evidence before and during launch.
Scripts + Message Templates: standardize provider recruitment, forwarding, offers, and ratings.

## Slide 27
Provider Form
Provider Signup Form — Part 1
Copy into Google Forms. Use this to collect basic provider identity and contact details.
Provider Form
27
Field
Input / Notes
Full name
Short answer. Legal name or complete name.
Display name
Short answer. Name that may be shown to clients.
Contact number
Short answer. Required for pilot coordination.
Messenger / Facebook link
Short answer. Preferred for fast communication.
Barangay / area
Short answer or dropdown. Helps match by location.
Preferred contact channel
Multiple choice: Messenger, SMS, Call, Email, Other.
Best time to contact
Short answer. Example: 6 PM–9 PM.
Provider type
Multiple choice: Individual, Freelancer, Shop, Small team, Business.

## Slide 28
Provider Form
Provider Signup Form — Part 2
Service details, skills, coverage, and availability.
Provider Form
28
Field
Input / Notes
Main service category
Dropdown: Appliance, Plumbing, Electrical, Computer, Motorcycle, Carpentry, Cleaning, Digital, Other.
Specific services offered
Paragraph. Ask for exact jobs they can do.
Years of experience
Multiple choice: Less than 1, 1–2, 3–5, 6–10, 10+.
Coverage area
Checkboxes or paragraph. Barangays/areas they can serve.
Emergency availability
Multiple choice: Yes, No, Sometimes.
Available days
Checkboxes: Mon, Tue, Wed, Thu, Fri, Sat, Sun.
Available time
Short answer. Example: evenings only, weekends, whole day.
Travel limits
Short answer. Maximum distance or areas not covered.

## Slide 29
Provider Form
Provider Signup Form — Part 3
Pricing, work proof, verification, and consent.
Provider Form
29
Field
Input / Notes
Minimum service fee
Short answer. Example: PHP 300 inspection fee.
Price range examples
Paragraph. Ask for common prices for typical jobs.
Work sample photos
File upload or link. Photos of finished work, tools, or shop.
Certificate / training proof
Optional file upload or link.
Valid ID for verification
Optional during pilot; required for Identity Verified badge.
Consent to receive job requests
Yes/No. Required.
Consent to receive ratings
Yes/No. Required.
Agreement to provider rules
Checkbox: I understand and agree.

## Slide 30
Provider Sheet
Provider Database Sheet — Columns 1
Use one row per provider. This is the main supply database.
Provider Sheet
30
Field
Input / Notes
Provider ID
Unique ID. Example: PROV-0001.
Date joined
Date provider was added.
Full name / Display name
Keep private/public name separate.
Contact number / Messenger link
Use for coordination.
Barangay / Area
Primary location.
Category / Specific skills
Main service and detailed services.
Years of experience
Trust signal.
Coverage area
Where provider can serve.

## Slide 31
Provider Sheet
Provider Database Sheet — Columns 2
Track responsiveness, quality, and provider status.
Provider Sheet
31
Field
Input / Notes
Availability / Emergency availability
When provider can accept jobs.
Minimum fee / price range
Helpful for matching and client expectations.
Work sample link
Google Drive or folder link.
Verification level
Listed, Identity Verified, Work Verified, Top Rated, Certified/Business Verified.
Requests received / replies
Count requests sent and provider replies.
Response rate / average response time
Helps identify reliable providers.
Jobs completed / average rating
Trust and performance record.
Status / notes
Active, inactive, warning, suspended, removed.

## Slide 32
Client Form
Client Request Form — Part 1
Copy into Google Forms. Use this to collect clear service requests.
Client Form
32
Field
Input / Notes
Client name or nickname
Short answer. Nickname is okay during pilot.
Contact number or Messenger
Short answer. Required for coordination.
Barangay / area
Short answer or dropdown.
Exact location notes
Optional paragraph. Do not forward full address too early.
Service category needed
Dropdown using the approved pilot categories.
Problem description
Paragraph. Ask what happened, when it started, and what help is needed.
Urgency level
Emergency, Today, This Week, Flexible, Scheduled.
Preferred schedule
Short answer. Example: today after 3 PM.

## Slide 33
Client Form
Client Request Form — Part 2
Budget, evidence, permission, and consent.
Client Form
33
Field
Input / Notes
Budget range
Multiple choice or short answer. Example: PHP 500–800.
Photos/videos of problem
File upload or link. Strongly recommended.
Permission to forward request
Yes/No. Required before contacting providers.
Can KAILA contact you for clarification?
Yes/No. Required.
Can provider contact you after selection?
Yes/No. Required for matching.
Willing to rate after completion?
Yes/No. Important for trust system.
Data privacy consent
Checkbox: I allow KAILA to use my submitted details for pilot matching.
Additional notes
Paragraph. Anything providers should know.

## Slide 34
Request Tracker
Request Tracker Sheet — Columns 1
Use one row per client request. This is the evidence tracker.
Request Tracker
34
Field
Input / Notes
Request ID
Unique ID. Example: REQ-0001.
Date/time received
Important for response time.
Client name / contact method
Keep details private and organized.
Barangay / category
Helps measure demand by area and category.
Problem description
Clear summary of the need.
Urgency / budget
Used for matching and offer comparison.
Photo/video link
Optional evidence for provider estimate.
Request completeness
Complete, needs clarification, incomplete.

## Slide 35
Request Tracker
Request Tracker Sheet — Columns 2
Track matching, offers, job outcome, and issues.
Request Tracker
35
Field
Input / Notes
Providers contacted
Names or provider IDs contacted.
Time forwarded to providers
Used to calculate response time.
Offers received
Amounts, schedule, and notes.
Selected provider
Provider chosen by client.
Agreed amount
Final price before job starts.
Job status
Received, forwarded, accepted, in progress, completed, rated, cancelled, disputed.
Ratings / issue
Client rating, provider rating, dispute or issue.
Final notes
Lessons, follow-up, repeat client potential.

## Slide 36
Job Log
Completed Job Log Template
Record completed or strongly matched jobs.
Job Log
36
Field
Input / Notes
Job ID / Request ID
Use both IDs for easy tracing.
Client / Provider
Name or assigned ID.
Category
Service category.
Agreed amount
Final amount used for GMV.
Date posted / accepted / completed
Used for timing metrics.
Client rating / provider rating
Two-way trust data.
Issue encountered
No issue, price change, delay, quality, no-show, communication, other.
Repeat client / notes
Would client use again? Would provider accept again?

## Slide 37
Dispute Log
Dispute Log Template
Use factual records only. Avoid emotional language.
Dispute Log
37
Field
Input / Notes
Dispute ID / Job ID
Unique ID and related job.
Complaint by
Client, provider, or KAILA operations.
Issue type
No-show, price change, poor quality, damage, payment, scope, rude communication, other.
Date reported
When issue was raised.
Description
Neutral summary of what happened.
Evidence collected
Request details, chats, photos, offer amount, agreed scope, completion confirmation.
Current status
Open, under review, resolved, closed, escalated.
Action taken / resolution
Warning, no action, restriction, status downgrade, suspension, removal.

## Slide 38
Survey Form
Client Survey Form — Part 1
Use before and during pilot to validate demand.
Survey Form
38
Field
Input / Notes
Name or nickname
Optional but useful for follow-up.
Barangay / area
Helps identify demand geography.
Age range
Optional demographic grouping.
In the past 6 months, did you need a service provider?
Yes/No.
What service did you need?
Appliance, plumbing, electrical, computer, motorcycle, cleaning, digital, other.
How did you look for that person?
Referral, Facebook, Messenger, neighbor, shop, previous provider, other.
How long did it take?
Same day, 1–2 days, 3–7 days, more than a week, never found one.
What was the hardest part?
Paragraph. Capture pain point in their words.

## Slide 39
Survey Form
Client Survey Form — Part 2
Trust, price, and willingness to use KAILA.
Survey Form
39
Field
Input / Notes
Did you compare prices?
Yes/No.
Was the price clear before the job started?
Yes/No/Somewhat.
What made you trust the provider?
Referral, known person, reviews, work samples, ID, shop, price, other.
Were you satisfied with the work?
1–5 rating or Yes/No.
Would you post a request in KAILA?
Yes/No/Maybe.
Would you upload photos/videos?
Yes/No/Maybe.
Would you compare offers from providers?
Yes/No/Maybe.
Would you rate the provider after completion?
Yes/No/Maybe.

## Slide 40
Interview Form
Provider Interview Form — Part 1
Use for deeper provider understanding beyond signup.
Interview Form
40
Field
Input / Notes
What services do you offer?
Ask for specific jobs, not just category name.
How many years have you done this work?
Experience background.
How do clients usually find you?
Referral, Facebook, shop walk-ins, repeat clients, other.
How many jobs do you get weekly?
Estimate normal workload.
Do you want more clients?
Yes/No/Depends. Ask why.
What areas can you cover?
Barangays, city limits, travel fee rules.
Which jobs are most profitable?
Useful for category prioritization.
Which jobs do you avoid?
Avoid poor matches and disputes.

## Slide 41
Interview Form
Provider Interview Form — Part 2
Offer behavior, verification, concerns, and platform trust.
Interview Form
41
Field
Input / Notes
Can you receive requests through Messenger/SMS?
Preferred channel and response habit.
Are you comfortable submitting offers?
Yes/No/Maybe. Ask concerns.
How do you estimate price?
Inspection fee, fixed fee, parts/labor, scope-based.
What makes a client difficult?
No-show, unclear scope, low budget, delayed payment, rude behavior.
What verification steps are acceptable?
ID, work samples, references, certificate, shop photo, pilot job history.
What concerns do you have about ratings?
Fear of unfair reviews, public complaints, client abuse.
What would make KAILA valuable to you?
More jobs, better clients, visibility, trust badge, performance summary.
Would you recommend another provider?
Ask for two referrals.

## Slide 42
Scripts
Provider Recruitment Script
Use this when contacting potential providers.
Scripts
42
Short message
Good day! We are starting KAILA, a local pilot platform that helps people in Gingoog find trusted service providers like repairmen, electricians, plumbers, computer technicians, motorcycle mechanics, cleaners, and digital workers. The pilot is free. We will list reliable providers so clients can find you more easily. When a client has a request, we may contact you. You can accept, decline, or give your own offer. Would you like to be included as one of the early KAILA providers?
Follow-up
If yes, I can send you a short provider signup form. It asks about your services, area covered, availability, price range, and work samples so we can match you with the right requests.

## Slide 43
Scripts
Client Request Confirmation Script
Send after a client submits a request.
Scripts
43
Confirmation
Thank you for submitting your request to KAILA. We will review the details and look for matching providers. We may contact you if we need more information. Please note that this is still a pilot, and providers are independent service providers.
Clarification
To help providers estimate better, please send a clear photo/video of the problem, your preferred schedule, and your estimated budget range if you have not included them yet.

## Slide 44
Scripts
Provider Request Forwarding Script
Send to 3–5 matching providers for each request.
Scripts
44
Request format
KAILA Request #001
Category: Plumbing
Area: Barangay 23, Gingoog City
Problem: Clogged kitchen sink
Urgency: Today
Budget: PHP 500–PHP 800
Can you take this job? If yes, please send your offer and available time.
Operating note
Do not share unnecessary private client details too early. Record who replies, how fast they reply, offer amount, available time, and any scope notes.

## Slide 45
Templates
Offer Comparison Template
Use this when presenting options to the client.
Templates
45
Field
Input / Notes
Provider A
Offer: PHP 600 | Available: 2 PM today | Trust: Listed | Notes: Has plumbing experience.
Provider B
Offer: PHP 750 | Available: 5 PM today | Trust: Work Verified | Notes: Has previous job photos.
Provider C
Offer: PHP 500 | Available: Tomorrow | Trust: Identity Verified | Notes: Lower price but not available today.
Client instruction
Please choose the provider you prefer. Final scope and price should be clear before work starts.

## Slide 46
Scripts
Completion and Rating Templates
Collect two-way ratings after the job.
Scripts
46
Client rating message
Hello! Was the job completed? Please rate the provider from 1 to 5 and share any comments about the service. Was the agreed price followed? Would you use KAILA again?
Provider rating message
Hello! Was the job completed? Please rate the client from 1 to 5 and share if there were any issues. Would you accept KAILA requests again?

## Slide 47
Rules
Provider Rules Agreement
Each provider should agree before receiving pilot requests.
Rules
47
☐ Respond honestly and only accept jobs you can perform.
☐ Give clear price or estimate before the job starts.
☐ Do not unfairly change price after arrival unless scope changes.
☐ Communicate delays early.
☐ Respect client property and privacy.
☐ Do not harass, threaten, pressure, or abuse clients.
☐ Allow KAILA to track job outcome during the pilot.
☐ Accept that ratings and reviews are part of the trust system.

## Slide 48
Rules
Client Reminders Template
Explain these before matching the client with a provider.
Rules
48
☐ KAILA is a pilot matching system.
☐ Providers are independent service providers, not KAILA employees.
☐ Clear descriptions and photos help providers estimate better.
☐ Final price and scope should be agreed before work starts.
☐ Scope changes may affect price.
☐ Client should confirm completion after the job.
☐ Client should give a fair rating after completion.
☐ Issues should be reported honestly with details and evidence.

## Slide 49
Weekly Report
Weekly Metrics Summary Template
Use this after every weekly review.
Weekly Report
49
Field
Input / Notes
Week covered
Start date to end date.
Providers joined / active
Total listed, active, inactive, category coverage.
Client requests
Total requests, top categories, top barangays, urgency mix.
Matching performance
Providers contacted, offers per request, average response time, accepted jobs.
Job outcomes
Completed jobs, strongly matched jobs, cancelled requests, no-response requests.
Trust and quality
Average ratings, disputes, complaints, top provider issues.
GMV
Total peso value of completed jobs.
Next actions
Owner, task, deadline.

## Slide 50
Weekly Report
Weekly Meeting Notes Template
Use this for founder/team meetings.
Weekly Report
50
Field
Input / Notes
Date and attendees
Who joined the meeting.
Decisions made
List each decision clearly.
Assumptions tested
What was proven or disproven this week?
Metrics reviewed
Providers, requests, offers, jobs, ratings, disputes, GMV.
Problems found
Top 3 operational or trust issues.
Lessons learned
What changed because of this week’s evidence?
Next actions
Task, owner, deadline, status.
Open questions
Items to test next week.

## Slide 51
Scorecard
Go / No-Go Scorecard — Part 1
Use after the 30–45 day active matching pilot.
Scorecard
51
Field
Input / Notes
Providers recruited
Target: 50 listed providers. Score 0–5.
Active provider rate
How many providers actually reply? Score 0–5.
Client responses
Target: 100 survey responses or strong early evidence. Score 0–5.
Real requests
Target: 30 real requests. Score 0–5.
Offers per request
Target: ideally 2–5 offers per good request. Score 0–5.
Completed / strongly matched jobs
Target: 15+. Score 0–5.

## Slide 52
Scorecard
Go / No-Go Scorecard — Part 2
Rate trust, quality, and operational feasibility.
Scorecard
52
Field
Input / Notes
Ratings behavior
Clients and providers accept two-way ratings. Score 0–5.
Disputes manageable
Disputes are low or manageable with clear records. Score 0–5.
Category strength
At least 2–3 categories show real activity. Score 0–5.
Operations workload
Team can support manual matching. Score 0–5.
Repeat potential
Clients/providers would use KAILA again. Score 0–5.
Decision rule
Proceed if evidence is strong; narrow if only few categories work; redesign/pause if trust or participation is weak.

## Slide 53
Pilot Report
Final Pilot Report Template — Part 1
Prepare this before deciding whether to build the MVP.
Pilot Report
53
Field
Input / Notes
Executive summary
Brief result: proceed, narrow, redesign, or pause.
Pilot area and dates
Barangays covered and active matching period.
Provider results
Total providers, active providers, categories covered, top providers.
Client validation results
Survey count, strongest pain points, willingness to use KAILA.
Request results
Total requests, category distribution, barangay distribution, urgency mix.
Matching results
Providers contacted, response rate, offers per request, time to first response.

## Slide 54
Pilot Report
Final Pilot Report Template — Part 2
Include financial, trust, and recommendation details.
Pilot Report
54
Field
Input / Notes
Job outcomes
Completed jobs, strongly matched jobs, cancelled requests, no-response requests.
GMV
Total value of completed jobs.
Ratings and trust
Average client rating, provider rating, comments, trust issues.
Disputes
Number, types, actions taken, unresolved issues.
Best categories
Categories with strongest demand and provider response.
Recommended next move
Proceed to MVP, narrow categories, extend pilot, redesign, or pause.

## Slide 55
MVP Template
MVP Feature Backlog Template
Use only after strong validation signals.
MVP Template
55
Field
Input / Notes
Feature
Short name of feature. Example: Client request posting.
User role
Client, provider, admin, operations.
Pilot evidence
Which manual workflow proved this feature is needed?
Priority
Must have, should have, later.
Acceptance criteria
How to know the feature works.
Risks
Privacy, safety, complexity, cost, or adoption risks.
Do not build yet
Payments, GPS tracking, native apps, complex AI matching, large automation.

## Slide 56
Monetization Template
Provider Visibility Offer Template
Draft only after providers feel real value from KAILA.
Monetization Template
56
Field
Input / Notes
Free provider profile
Basic listing, can receive requests, basic category inclusion.
Premium provider profile
Featured placement, better profile layout, more work photos, trust badge display.
Monthly performance summary
Requests received, replies, jobs completed, ratings, response speed.
Facebook feature
Optional featured post for trusted active providers.
Badge display
Identity Verified, Work Verified, Top Rated, Certified/Business Verified.
Important rule
Do not charge until usage and trust are proven. Avoid commission as the first paid product.

## Slide 57
Operations Template
Folder and File Structure Template
Keep files organized from Day 1.
Operations Template
57
Field
Input / Notes
01_Admin
Founder notes, decision log, budget, meeting notes.
02_Provider_Database
Provider sheet, provider forms, work samples, verification tracker.
03_Client_Requests
Request tracker, request photos/videos, request summaries.
04_Job_Logs
Completed job log, ratings, GMV tracker.
05_Disputes
Dispute log, evidence, actions taken.
06_Marketing
Facebook posts, logo, graphics, provider features.
07_Reports
Weekly summaries, pilot report, scorecards.
08_MVP_Planning
Feature backlog, database notes, wireframes, build plan.

## Slide 58
Checklist
Quality Check Before Launch
Use this before accepting public requests.
Checklist
58
☐ Facebook page is ready and understandable.
☐ Provider form and provider sheet are tested.
☐ Client request form and request tracker are tested.
☐ Provider rules and client reminders are written.
☐ At least 20 providers have been contacted.
☐ First provider profiles are grouped by category.
☐ Request forwarding script is ready.
☐ Offer comparison, completion, and rating templates are ready.

## Slide 59
Targets
Final Success Targets
Use these as the first-pilot evidence targets.
Targets
59
50 providers
Target supply base
100 client responses
Demand validation
30 real requests
Live pilot demand
15 completed / matched jobs
Minimum strong evidence
5–8 categories
Focused service scope
30–45 days
Active matching period

## Slide 60
Final Reminder
Do not build the full KAILA app yet.
Build proof first: provider list, client request form, request tracker, manual matching, offer comparison, completion confirmation, rating process, weekly review, and go/no-go decision.
Once this works, the MVP becomes easier because it is built from actual behavior.
KAILA
60